Communications Plan		  	    Project Deadline: _September 30, 2018

Project Name: __Hep A awareness_____________  Start Date: ___June 6, 2018_________

Project Coordinator(s):___Kristina, Helen, Tamara, Sue, Cindy, Julie_____________________

OCDPH Section:

Community Health	   Clinical Services       Environ. Health       Epidemi.        Other

MIHP				Immuniz.	              Food Svc	           ____________________________________

Child Health		CD   	  		    On-site

Oral Health			Sex Health		    Solid Waste	____________________________________

Health Promo

Budget: ____~$5,000_______________________________________________________________

Grant Requirements: ____Hep A messaging___________________________________________

COM Description:

Timing:      Proactive        Reactive	     Type:      Inform for Decision	     Persuade for Change

Target Audience:

Internal:     Staff         Administration	  County-wide	   __________________________________________

External:	    Parents        Youth	    General Community        Media	      Policymaker        _  High risk _________(MSM, drug users, transient/homeless, recent jail/prison, underlying liver disease)___________

Demographics: Age:_25-55__   Gender: _Male_   Culture: __high-risk___  Language: __English_____

Region: _Holland, Allendale, Hudsonville, Georgetown_______   Preferred COM method: __In-person, social media, print

Problem to Address: __Continued Hep A outbreak across the state resulting in hospitalizations and death. __Low public awareness of outbreak, seriousness of Hep A and how to prevent it. _____________

Desired Outcome(s):   	Behavior Change       Awareness	    Prevention        Policy Change  Desired Action/Response:___Wash hands and get vaccinated__________________________________

Potential Barriers or Special Needs: ___Reaching homeless/transient populations via paid advertising – will need information in person _________________________________________________

Data/Research: (Reports, Surveys, Rankings, Numeric Analogy, Case Studies, Focus Groups or Visual Stats) __www.michigan.gov/HepAoutbreak / https://www.michigan.gov/mdhhs/0,5885,7-339-71550_2955_2976_82305_82310-447907--,00.html ________________________________________________ __https://www.cdc.gov/hepatitis/hav/afaq.htm _______________________________________________

Partners: (schools, advocacy groups, policymakers, religious org, healthcare org, specialist, community org, businesses) _____MDHHS and other LHDs for shared resources ___________________________________________

Key Message(s):

Stop the MI Hepatitis A outbreak

Wash your Hands

Get Vaccinated

Additional Notes & Resources: (existing promo material, personal/success stories, quotes, images/photos, analogies/metaphors, word clusters, infographics, etc.)

Develop consistent theme/look across all deliverables (colors, fonts, photos/graphics).

Share finalized assets with MDHHS and MiPIO Network.

Marketing Schedule

| Phase | Date | Description | Deadline Date | Hours worked on project |
| --- | --- | --- | --- | --- |
| Develop COM plan | June 6 | Met with team to determine budget, select outreach options based on target audience | - |  |
| Review 1st Proof(s) | June 12 | Sent concept to team for review | June 14 |  |
| Review 2nd Proof(s) | ongoing |  | ongoing |  |
| Review 3rd Final Proof(s) |  |  |  |  |
| Wrap-up/Evaluation |  |  | Sept 30 |  |

| Deliverables | Budget | Assigned to | Target Delivery Date | Notes | Completed |
| --- | --- | --- | --- | --- | --- |
| GovDelivery email bulletin | 0 | KW | Aug & Sept | Send to relevant subscribers |  |
| News Release/PSA/Op-Ed | 0 | KW | TBD |  |  |
| miOttawa Website | 0 | KW | Done | Hot Topics – CDC microsite **Pull analytics | X |
| Social Media Ads | $1,250 | KW | Aug-Sept | Facebook/Instagram Google/YouTube | X |
| Online Blogs or Comments |  |  |  |  |  |
| Online Event Calendars | 0 | CB | TBD | Post on-site clinic dates |  |
| Radio Appearances |  |  |  |  |  |
| TV Appearances |  |  |  |  |  |
| Paid TV Ads |  |  |  |  |  |
| Paid Radio Ads |  |  |  |  |  |
| Paid Print Ads | $210 | KW | July 17 | ¼ page ads in Revue magazine (Aug & Sept) | X |
|  | $750 | KW | July-Sept | Johnny Ads (Ottawa County only in bars/restaurants, men’s restrooms) | X |
| Postcards/Coupons | 0 | KW | TBD | Print in house (or get printer quotes) |  |
| White/Fact Sheets |  |  |  |  |  |
| Pamphlet/Brochure |  |  |  |  |  |
| Posters/Flyers/Rack Cards | 0 | KW | July | Create printable/sharable for bulletins and clinics | X |
| Banners |  |  |  |  |  |
| Promo Products |  |  |  |  |  |
| Signage | $1,520 | KW | July-Sept | Max Bus (4 interior and 3 exterior boards - 3 months, includes printing cost) | X |
| Billboards | $1,480 | KW | June-Aug | Lamar (2 boards – 4 weeks each) | X |
| Presentations & Conferences |  |  |  |  |  |
| Infographic | 0 | KW | July | Updated MDHHS to match campaign | X |
| Video Production (YouTube) | 0 | KW | July | Create 15sec video for social media ads and lobby tv | X |
| Audio Recording (podcast) |  |  |  |  |  |
| Administrator’s Digest |  |  |  |  |  |
| Community Resource 2-1-1 | 0 | KW | June | Updated with info on where to get Hep A vaccine | X |
| Other |  |  |  |  |  |
| TOTAL | ~$5,210 |  |  |  |  |

15 second video - https://youtu.be/SKWS5t9wKGM